## Project Plan
Create a Work Plan in this worksheet. The title of this worksheet is in cell C1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. |  | ArlaxKnowit Friday Bar 2025 - Project Plan
Phase headings are in cells C2, D2, E2 and F2. There is an arrow shape in each cell with the text “Phase 1”, “Phase 2”, “Phase 3” and “Phase 4” in them, in addition to cell text, which is hidden behind each shape. Each phase has corresponding activities and outcomes that are listed below each heading.
Titles for each phase are listed in this row from cells C3 to F3. Overwrite or delete the sample data to create your own titles. |  | April | May | June | July | August | September | October
Activities for each phase are listed in the table starting in cell C4. Column B contains the word Activity in hidden text. This helps you navigate the table with a screen reader. Some screen readers will read the text as you navigate to other rows so you don’t get lost between tables in this worksheet. Sample text for each phase is in columns C4 to F4. Enter your own list of activities for each phase in the Activites table. A shape overlaps column B with the word “Activities” as a visual representation of what is contained in this table. Continue to cell A11 for the next instruction. | Activity | Find video maker | Decide date | Plan activities, buy | Plan activities, buy | Plan activities, buy | Send out invitation Reminder+Event Details (1 week before event) ? | Send out Thank you email+Aftermovie (2-3 weeks after event)
| Activity |  | Update guestlist (max mid-May) | Discuss ideas/merchandise | Discuss ideas/merchandise | Find video maker | Creation of aftermovie
| Activity |  | Creation of 1st invitation |  | Creation of reminder invitation | Find someone that will record on the day
| Activity |  | Send out invitation (late May) |  |  | Creation of reminder invitation
| Activity |  | Discuss ideas/merchandise |  |  | Send out reminder invitation
| Activity |  | Plan activities, buy
This row marks the end of the sample table “Activities”. To add more Activities for any of the phases, simply add new rows above this one. Continue to cell A13 for the next instruction.
Titles for each Outcome for the above phases are listed in this row from cells C13 to F13. Overwrite or delete the sample data to create your own titles. |  | April | May | June | July | August | September | October
Outcomes for each phase are listed in the table starting in cell C14. Column B contains the word Outcome in hidden text. This helps you navigate the table with a screen reader. Some screen readers will read the text as you navigate to other rows so you don’t get lost between tables in this worksheet. Sample text for each phase is in columns C14 to F14. Enter your own list of outcomes for each phase in the Outcomes table. A shape overlaps column B with the word “Outcomes” as a visual representation of what is contained in this table. Continue to cell A19 for the next instruction. | Outcome | Update guestlist | Send invitation | Send invitation | Send invitation | Send invitation |  | Send out Thank you email+Aftermovie (2-3 weeks after event)
| Outcome | Book meeting rooms for 12/09
| Outcome | Send invitation
This row marks the end of the sample table “Outcomes”. To add more Outcomes for any of the phases, simply add new rows above this one.
|  | April | May | June | July | August | September | October
| Outcome | Update guestlist | Send invitation | Send invitation | Send invitation | Send invitation |  | Send out Thank you email+Aftermovie (2-3 weeks after event)
| Outcome | Send invitation
Outcome
|  | April | May | June | July | August | September | October
| Outcome | Update guestlist | Send invitation | Send invitation | Send invitation | Send invitation |  | Send out Thank you email+Aftermovie (2-3 weeks after event)
| Outcome | Send invitation
Outcome
|  | April | May | June | July | August | September | October
| Outcome | Update guestlist | Send invitation | Send invitation | Send invitation | Send invitation |  | Send out Thank you email+Aftermovie (2-3 weeks after event)
| Outcome | Send invitation
Outcome
|  | April | May | June | July | August | September | October
| Outcome |  |  | Food and drinks | Food and drinks | Food and drinks
Outcome
Outcome
|  | April | May | June | July | August | September | October
| Outcome |  | Gifts | Food and drinks | Food and drinks | Food and drinks
| Outcome |  | Activities | Gifts | Gifts | Gifts
| Outcome |  |  | Activities | Activities | Activities
|  | April | May | June | July | August | September | October
| Outcome | Creation of invitation | Creation of invitation | Creation of invitation | Creation of invitation | Creation of invitation | Creation of aftermovie | Creation of aftermovie
| Outcome | Video maker (confirmed availability) | Merchandise design | Merchandise design
Outcome
|  | April | May | June | July | August | September | October
| Outcome |  | Creation of sign up in Hubspot | Creation of sign up in Hubspot | Creation of sign up in Hubspot | Creation of sign up in Hubspot | Send out Thank you email+Aftermovie (2-3 weeks after event) | Send out Thank you email+Aftermovie (2-3 weeks after event)
| Outcome |  | Creation of invitation | Creation of invitation | Creation of invitation | Creation of invitation
Outcome
|  | April | May | June | July | August | September | October
| Outcome | [5 empty] | Video recorder on the day? | Video recorder on the day?
Outcome
Outcome
Overview
Anne F.
Pernille
Hans
Benjamin
Tinne/Camilla
Katharina
Edoardo
Anne S.
X (Maria Bak?)